## Gantchart
GANTT CHART
PROJECT TITLE |  | Simple Social Media Platform to connect with college peers |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT GUIDE |  | Dr. Pravin Adivarekar |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Problem search | Devansh, Riddhi | 2020-05-10 | 20/10/2020 | 3 | 100% | bar: WEEK 1 M to WEEK 1 T; WEEK 2 M to WEEK 2 R; WEEK 3 T to WEEK 3 R
1.1.1 | Problem finalization | Devansh, Riddhi, Aditya, Shauryan | 2020-07-11 | 2020-07-11 | 1 | 100% | bar: WEEK 1 M; WEEK 2 W
1.2 | Project Title | Riddhi | 20/11/2020 | 20/11/2020 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
1.3 | Abstract | Riddhi | 20/11/2020 | 23/11/2020 | 2 | 100% | bar: WEEK 1 F; WEEK 2 R to WEEK 2 F
1.4 | Problem Definition | Devansh, Riddhi | 2020-10-11 | 23/11/2020 | 1 | 100%
1.5 | Objectives | Devansh, Riddhi | 2020-10-11 | 23/11/2020 | 1 | 100%
1.6 | Scope | Riddhi | 2018-03-23 | 2020-08-30 | 1 | 100%
1.7 | Existing System/Project | Riddhi | 2020-10-11 | 2020-10-11 | 1 | 75%
1.8 | Technology stack | Devansh, Aditya, Shauryan | 20/11/2020 | 23/11/2020 | 1 | 90%
1.9 | Benefits for environment | Riddhi | 2020-10-12 | 15/12/2020 | 1 | 100%
1.1 | Benefits for society | Riddhi | 2019-08-23 | 15/12/2020 | 1 | 100%
1.11 | Applications | Devansh, Riddhi | 2019-08-23 | 15/12/2020 | 1 | 70%
2 | Project Design
2.1 | Proposed System | Shauryan, Aditya, Devansh | 2019-09-19 | 15/12/2020 | 1 | 80%
2.2 | Design(Flow Of Modules) | Devansh, Aditya, Shauryan | 2019-09-19 | 15/12/2020 | 1 | 70%
2.3 | Data Flow Diagram | Devansh, Aditya, Shauryan | 2019-09-19 | 15/12/2020 | 1
2.4 | Modules
2.4.1 | Module-1
2.4.2 | Module-2
2.4.3 | Module-3
2.4.4 | Module-4
2.5 | Preparation Of Report | Riddhi, Aditya, Shauryan | 2020-10-12 | 15/12/2020 |  | 40%
3 | Project Implementation
3.1 | Module-1
3.2 | Module-2
3.3 | Module-3
3.4 | Module-4
4 | Testing
4.1 | Design of Test Cases
4.2 | Testing
5 | Results and Analysis
5.1 | Analysis Of Results
5.2 | Graphical Representation
5.3 | Report Preparation