## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Simple Social Media Platform to connect with college peers |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT GUIDE |  | Dr. Pravin Adivarekar |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Problem search | Devansh, Riddhi | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Problem finalization | Devansh, Riddhi, Aditya, Shauryan | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Riddhi | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Riddhi | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Problem Definition | Devansh, Riddhi | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Objectives | Devansh, Riddhi | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Scope | Riddhi | 2018-03-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
1.7 | Existing System/Project | Riddhi | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Shauryan, Aditya | 2019-08-23 | 2019-08-30 | 1 | 80% | bar: WEEK 3 F
1.9 | Benefits for environment | Devansh, Riddhi | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Devansh, Riddhi | 2019-08-23 | 2019-08-30 | 1 | 80% | bar: WEEK 3 F
1.11 | Applications | Devansh, Riddhi | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Akshay, Nirish, Tarkeshwar | 2019-09-19 | 2019-09-27 | 1 | 70% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Akshay, Nirish | 2019-09-19 | 2019-09-27 | 1 | 70% | bar: WEEK 4 F to WEEK 5 F
2.3 | Data Flow Diagram | Nirish | 2019-09-19 | 2019-09-27 | 1 | 50%
2.4 | Modules | Nirish | 2019-09-19 | 2019-09-27 | 1 | 50%
2.4.1 | Module-1 | Akshay | 2019-09-19 | 2019-09-27 | 1 | 30%
2.4.2 | Module-2 |  | 2019-09-19 | 2019-09-27 | 1
2.4.3 | Module-3 |  | 2019-09-19 | 2019-09-27 | 1
2.4.4 | Module-4 |  | 2019-09-19 | 2019-09-27 | 1
2.5 | Preparation Of Report |  | 2019-09-19 | 2019-09-27 | 1
3 | Project Implementation
3.1 | Module-1 | X |  |  | 0 | 0%
3.2 | Module-2 | Y |  |  | 0 | 0%
3.3 | Module-3 | Y |  |  | 0 | 0%
3.4 | Module-4 | Z |  |  | 0 | 0%
4 | Testing
4.1 | Design of Test Cases | Y |  |  | 0 | 0%
4.2 | Testing | Y |  |  | 0 | 0%
5 | Results and Analysis
5.1 | Analysis Of Results | Y |  |  | 0 | 0%
5.2 | Graphical Representation | Y |  |  | 0 | 0%
5.3 | Report Preparation